## Main Table
Task | Optimistic | Nominal | Pessimistic | µ | σ | Total µ | Total σ
Alpha | 1 | 3 | 12 | 4.1667 | 1.8333 | 14.1667 | 3.1358
Beta | 1 | 1.5 | 14 | 3.5 | 2.1667
Gamma | 3 | 6.25 | 11 | 6.5 | 1.3333
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
Note on B1: Author: Optimistic Estimate. This number is wildly optimistic. You could only get the task done this quickly if absolutely everything went right.
Note on C1: Author: Nominal Estimate. This is the estimate with the greatest chance of success.
Note on D1: Author: Pessimistic Estimate. This is wildly pessimistic. It should include everything except hurricanes, nuclear war, stray black holes, and other catastrophes.
Note on E1: Author: Probability distribution of the expected duration for each task.
Note on F1: Author: Standard deviation of the probability distribution for each task. It is a measure of how uncertain the task is. When this number is large, the uncertainity is large too.